## Sheet1
OpenWeather++ Implementation Plan
Section | Task | Assigned Member | Planned Start | Planned Finnished | Implemented Start | Implemented Finish
Weather Station Software Modules | Rain Gauge | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Wind Vane | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Wind Speed | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Tempurature | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Humidity | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Solar Intensity | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Barometric Pressure | Taylor Grimes | 2012-09-12 | 2012-09-17
| Lightning Detector | Taylor Grimes | 2012-09-18 | 2012-09-23
| GSM communication | Ismael Wayne | 2012-09-12 | 2012-09-23
Weather Station Hardware Design | Arduino Interface Sheild Circuit Design | Tyler | 2012-09-10 | 2012-09-10
| Components Housing System | Taylor Grimes
| Mounting System | Ismael Wayne
Weather Data Server API | MySQL Database Schema | Travis Cricthfield | 2012-09-10 | 2012-09-15
| PHP Backend | Travis Cricthfield | 2012-09-10 | 2012-09-14
| Client facing front end | Travis Cricthfield | 2012-09-10 | 2012-09-14
Weather Station Unit Test | Rain Gauge | Entire Team | 2012-09-24 | 2012-09-24
| Wind Vane | Entire Team | 2012-09-25 | 2012-09-25
| Wind Speed | Entire Team | 2012-09-26 | 2012-09-26
| Tempurature | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Humidity | Tyler | FINISHED | FINISHED | FINISHED | FINISHED
| Solar Intensity | Entire Team | 2012-10-01 | 2012-10-02
| Barometric Pressure | Entire Team | 2012-10-02 | 2012-10-03
| Lightning Detector** | Entire Team | 2012-10-03 | 2012-10-04
| GSM Communication | Entire Team | 2012-10-04 | 2012-10-05
Weather Data Server Test | Data API call in w/ Database Write | Ismael Wayne | 2012-09-11 | 2012-09-12
| Data Read from Database to Front End | Ismael Wayne | 2012-09-13 | 2012-09-14
Implemenation Test w/ Server | Test of full system functionality | Entire Team | 2012-10-15 | 2012-10-25
Deployment | System | Entire Team | 2012-11-01 | 2012-11-10
| Bug Tracking/Fixing | Taylor Grimes | 2012-11-01 | 2012-11-15
** Weather Permitting